## RFP Overview
c
Vendor Response Workbook ¦ APP-01548
| RFP Information | Details | Vendor Action
| Issuing Organization | Northwest Mississippi Regional Medical Center
| Project / Award | Phase 1 Maternal-Newborn Access Preservation and Modernization Readiness ¦ APP-01548
| Grant Initiative | Building Rural Infrastructure for Delivery, Growth, and Efficiency (BRIDGE)
| Project Location | 1970 Hospital Drive, Clarksdale, Mississippi 38614
| Issue Date | 2026-10-15
| Questions Due | 2026-10-30
| Proposal Due | 2026-11-15
| Anticipated Award | 2026-11-30
| Target Completion | No later than July 31, 2027, unless otherwise approved
1. Complete all blue-input cells.
2. Use the compliance dropdown on every technical requirement. Blank responses may be treated as noncompliant.
3. Enter unit prices on the Pricing sheet; extended prices and totals calculate automatically in Excel.
4. Describe all exceptions, exclusions, assumptions, dependencies, lead times, and optional costs.
5. Complete certifications and authorized signature information before submission.
PROPOSAL SUBMISSION & CONTACTS
| Proposal submission email | Jbedford@nwmrmc.org
| Evaluations / demonstrations contact | Jbedford@nwmrmc.org
| Questions and answers contact | Jeff Bedford, CFO
| Questions and answers email | Jbedford@nwmrmc.org
| Phone number | 662-624-3480

## Procurement Schedule
APP-01548 PROCUREMENT SCHEDULE
Maternal-Newborn Phase 1 Readiness Professional Services
Milestone | Date | Notes
RFP issued | 2026-10-15
Questions due | 2026-10-22
Proposal due | 2026-10-29
Anticipated award | 2026-11-12
Target completion | 2027-07-31 | No later than July 31, 2027, unless otherwise approved
PROPOSAL SUBMISSION & CONTACTS
Proposal submission email | Jbedford@nwmrmc.org
Evaluations / demonstrations contact | Jbedford@nwmrmc.org
Questions and answers contact | Jeff Bedford, CFO
Questions and answers email | Jbedford@nwmrmc.org
Phone number | 662-624-3480

## Vendor Information
VENDOR INFORMATION
Complete all applicable fields. Blue cells are vendor inputs.
Proposer Legal Name
Doing Business As
Street Address
City / State / ZIP
Primary Contact Name
Title
Email
Phone
Website
Federal Tax ID / EIN
SAM.gov UEI
Years in Business
Prime Firm / Joint Venture Status
Proposed Prime Contractor
Subcontractors (identify each)
Conflict of Interest Disclosure Status | Complete the “Conflict of Interest” worksheet and attach the signed form and applicable supporting documents.
RFP Exceptions Summary | Complete the RFP Exceptions worksheet and indicate No Exceptions or Exceptions Listed Below.
Proposal Validity Date (minimum 120 days)
Proposal Submission Email | Jbedford@nwmrmc.org
Questions / Evaluations Contact | Jeff Bedford, CFO ¦ Jbedford@nwmrmc.org ¦ 601-927-5333

## Technical Compliance
SCOPE OF SERVICES COMPLIANCE MATRIX
Mark each item Comply, Partial, Alternative, or Exception. Explain the proposed approach and reference attachments.
# | Scope / Requirement | Minimum Requirement | Response | Proposed Technical Approach | Attachment Reference | Assumptions / Exceptions
1 | Project management and controls | Kickoff, responsibility matrix, communications, detailed workplan, baseline schedule, deliverable register, decision/risk logs, QC plan, monthly reporting, meeting records, and stakeholder coordination.
2 | Existing conditions and building-systems verification | Field verification; structural, envelope/moisture, HVAC, plumbing/water, medical gas, electrical/essential power, fire alarm, sprinkler, life safety, egress, evacuation, accessibility, maintainability, deficiencies, constraints, photographs, annotated drawings, priorities, and recommendations.
3 | Hazardous materials and infection-control readiness | Qualified hazardous-materials/asbestos evaluation, sampling and laboratory documentation, limitations/recommendations, and preliminary ICRA/TILSM or equivalent planning; no abatement or demolition unless separately authorized and allowable.
4 | Clinical programming and workflow | User sessions and room-by-room programs for LDRP/LDRPB, postpartum, well-baby and Level II nursery, C-section support, procedure/support areas, clean work, medication/Pyxis, nurse station, staff/storage/family spaces, adjacencies, utilities, security, emergency response, and workflow.
5 | FF&E and medical-equipment readiness | Equipment and FF&E matrices, utilities, infrastructure loads, clearances, dependencies, owner-furnished items, and future procurement recommendations; no equipment purchase under this RFP.
6 | Design development and future-phase bid documents | Advance authorized concept portions; coordinate architecture and engineering disciplines; prepare future Phase 2-5 drawings/specifications, alternates, package boundaries, phasing interfaces, long-lead and commissioning requirements; no current construction authorization.
7 | Code, regulatory, safety, and security readiness | Code/regulatory basis, life safety, egress, fire protection, accessibility, medical gas, utilities, water management, infection prevention, newborn security, emergency response, continuous operations, and anticipated agency pathway.
8 | Patient-care continuity and future phasing | Protect maternal-newborn capacity, C-section/emergency access, newborn stabilization, nursery/postpartum functions, supplies, utilities, egress, infection prevention, security, staff/family routing; define temporary measures, shutdown/outage controls, contingencies, go/no-go criteria, signoffs, and recovery.
9 | Cost validation and procurement readiness | Itemized estimate, quantities, unit costs, allowances, escalation, contingencies, alternates, owner costs, professional fees, testing, commissioning, temporary measures, exclusions, reconciliation, checklist, and competitive packaging strategy.
10 | OB access and readiness dashboard | Editable aggregate tracker for OB volume, service availability, clinic demand, milestones, deliverables, expenditures, risks, mitigation, decisions, procurement status, measures, and closeout; no patient-level PHI required.
11 | Baby-Friendly readiness | Design/workflow checklist addressing breastfeeding support, privacy, education, rooming-in/family-centered care, and newborn support.
12 | Grant reporting and closeout | Deliverable register, labor/subconsultant/expense and invoice support, status narratives, budget crosswalk, performance measures, editable files, PDFs, calculations, meeting/approval records, and final closeout package.
13 | Excluded scope acknowledgment | No active construction, demolition, new construction, major expansion, equipment purchase, telehealth, EHR, cybersecurity, broadband, provider payments, or lobbying under this award; future construction only as roadmap and bid packages.

## Deliverables & Milestones
REQUIRED DELIVERABLES & MILESTONES
Provide proposed delivery dates, acceptance approach, and attachment references.
No. | Deliverable | Target / Acceptance Basis | Proposed Delivery Date | Vendor Acceptance Approach | Attachment Reference
1 | Project management plan and baseline schedule | Within [10] business days after notice to proceed; subject to NWMRMC approval.
2 | Existing conditions and building-systems assessment | Discipline-coordinated report with annotated plans, photographs, findings, priorities, and recommendations.
3 | Hazardous-materials/asbestos evaluation | Sampling plan, reports, laboratory documentation, limitations, and future-action recommendations.
4 | Clinical room program and workflow package | Approved room data, adjacency/workflow diagrams, meeting records, and decision log.
5 | FF&E and medical-equipment readiness package | Equipment/FF&E matrices, utility/infrastructure requirements, ownership and procurement assumptions.
6 | Code, life-safety, regulatory, infection-control, water-management, and newborn-security readiness packet | Basis-of-design, issues matrix, agency pathway, preliminary controls, and approvals.
7 | Design development package | Coordinated plans, narratives/specifications, calculations, decisions, and QC record.
8 | Future Phase 2-5 bid documents | Coordinated future-phase drawings/specifications, alternates, package boundaries, and transmittals as authorized.
9 | Validated cost estimate and procurement-readiness package | Reconciled estimate, assumptions, escalation, contingencies, alternates, checklist, and packaging strategy.
10 | Patient-care continuity and future-phasing plan | Operational plan with routes, temporary measures, shutdown controls, contingencies, security, signoffs, and go/no-go criteria.
11 | Baby-Friendly readiness checklist | Design/workflow criteria for breastfeeding support, privacy, education, family-centered care, and newborn support.
12 | OB access and readiness dashboard | Editable dashboard, data dictionary, source and ownership map, and monthly update process.
13 | Monthly status, invoice, and grant-support package | Status, schedule, risks/decisions, invoice detail, deliverable evidence, and budget crosswalk.
14 | Final closeout package | Accepted deliverables, editable files, PDFs, source records, approvals, financial support, and closeout narrative by contractual deadline.

## Price Proposal
FORM C - COST PROPOSAL
Provide a complete not-to-exceed fee by work package, including labor, subconsultants, expenses/testing, and all other costs.
Deliverable / Work Package | Labor ($) | Subconsultants ($) | Expenses / Testing ($) | Other Cost ($) | Total ($) | Notes / Assumptions
1. Project controls |  |  |  |  | 0
2. Existing conditions / building systems |  |  |  |  | 0
3. Hazardous materials / asbestos |  |  |  |  | 0
4. Clinical programming / workflow |  |  |  |  | 0
5. FF&E / medical equipment planning |  |  |  |  | 0
6. Code / regulatory / infection control |  |  |  |  | 0
7. Design development |  |  |  |  | 0
8. Future Phase 2-5 bid documents |  |  |  |  | 0
9. Cost validation / procurement readiness |  |  |  |  | 0
10. Continuity / phasing plan |  |  |  |  | 0
11. Dashboard / reporting / closeout |  |  |  |  | 0
TOTAL NOT-TO-EXCEED | 0 | 0 | 0 | 0 | 0
Proposal validity period (minimum 120 days)
Labor-rate schedule attachment
Travel and reimbursable assumptions
Optional services and pricing
Payment schedule / milestones
Contingency assumptions and exclusions

## Team & Subconsultants
FORM B - TEAM & SUBCONSULTANTS
Identify the prime firm and every subconsultant, discipline, credential, estimated participation, and office location.
Firm / Individual | Prime or Subconsultant | Discipline / Role | License / Credential | Estimated % | Office Location | Business Category, if volunteered

## Implementation Plan
IMPLEMENTATION, MIGRATION & RISK RESPONSE
Provide complete responses and attach supporting documentation where requested. Refer to Tab and number on Attachments example: "Imp Plan 6"
# | Requested Information | Vendor Response
1 | Understanding of project, grant boundary, active-care constraints, and desired outcomes
2 | Project management plan, responsibility matrix, communication, escalation, and project controls
3 | Detailed schedule for field work, programming, assessment, design, cost validation, continuity planning, dashboard, and closeout
4 | Quality-control method and discipline coordination
5 | Field verification and existing-conditions assessment approach
6 | Clinical user engagement and room-by-room programming approach
7 | Patient-care continuity, phasing, shutdown, infection control, and go/no-go planning
8 | Design development and future Phase 2-5 bid-document approach
9 | Cost validation and procurement-readiness approach
10 | OB dashboard, grant reporting, invoice support, and closeout approach
11 | Risks, assumptions, information required from NWMRMC, and mitigation

## Qualifications & References
VENDOR QUALIFICATIONS & REFERENCES
Provide complete responses and attach supporting documentation where requested and/or if applicable for ease of submission. Refer to Tab and number on Attachments example: "Ques & Ref 8"
# | Requested Information | Vendor Response
1 | Acute-care hospital planning/design and occupied healthcare environment experience
2 | Maternal-newborn, L&D, nursery, C-section support, or comparable experience
3 | Key personnel, disciplines, Mississippi licenses/credentials, availability, and resumes
4 | Reference 1: client/project, contact, services/dates, value, relevance
5 | Reference 2: client/project, contact, services/dates, value, relevance
6 | Reference 3: client/project, contact, services/dates, value, relevance
7 | Prime firm/subconsultant organization, roles, percentage of work, and office locations
8 | Insurance, federal eligibility, financial/technical capacity, and other responsibility information

## Warranty & Support
WARRANTY, SUPPORT & ESCALATION
Provide complete responses and attach supporting documentation where requested. Refer to Tab and number on Attachments example: "War & Sup 6"
# | Requested Information | Vendor Response
1 | Professional standard of care and correction of errors/omissions
2 | Project management and issue/escalation support
3 | Key-person availability and substitution controls
4 | Document quality-control and interdisciplinary coordination
5 | Site access, safety, infection prevention, and occupied-facility controls
6 | Record retention, audit cooperation, and grant-review support
7 | Ownership/license rights for drawings, models, reports, data, calculations, and editable files
8 | Closeout and future procurement support
9 | Insurance coverage and indemnity assumptions
10 | Transition support and availability for clarifications after closeout

## Submission Checklist
PROPOSAL SUBMISSION CHECKLIST
Provide complete responses and attach supporting documentation where requested. Refer to Tab and number on Attachments example: "Subm Checklist 6"
# | Requested Information | Status / Location in Proposal
1 | Signed cover letter and acknowledgment of all addenda
2 | Executive summary and understanding of project, grant boundary, and active-care constraints
3 | Completed scope-of-services compliance matrix
4 | Completed separate cost proposal with labor, subconsultants, expenses/testing, and all costs
5 | Project management plan, quality-control method, communications, escalation, and detailed schedule
6 | Prime firm/subconsultant organization, key-person resumes, licenses, and availability
7 | Qualifications and relevant project experience with references
8 | Assumptions, exclusions, required NWMRMC information, deviations, and contract exceptions
9 | Conflict-of-interest and organizational-conflict disclosures
10 | Federal eligibility, lobbying, responsibility, and vendor certifications
11 | Small/diverse/veteran/labor-surplus-area participation and outreach information
12 | Certification that proposal remains valid for at least 120 days

## Conflict of Interest
VENDOR CONFLICT OF INTEREST DISCLOSURE & ATTESTATION
NWMRMC Maternal-Newborn Phase 1 Readiness RFP ¦ APP-01548 ¦ RHTP
Complete and submit this disclosure with the proposal. Disclose every actual, potential, or apparent financial, family, business, employment, or personal interest involving NWMRMC, this procurement, or a proposed subcontractor. Disclosed matters must be reviewed and resolved or mitigated in writing, as applicable.
A. VENDOR INFORMATION
Vendor legal name
Business address
Authorized representative and title
Email and phone
Proposed subcontractor(s), if any
B. CONFLICT OF INTEREST QUESTIONS
# | Question | Yes / No | Explanation required for Yes
1 | Any actual, potential, or apparent relationship with an NWMRMC officer, employee, agent, board member, or immediate family member?
2 | Any ownership, compensation, employment, creditor, or other financial interest involving NWMRMC personnel and the vendor or subcontractor?
3 | Any gift, gratuity, favor, travel, hospitality, employment opportunity, compensation, or thing of value offered to influence this procurement?
4 | Any vendor involvement in preparing specifications, scope, evaluation criteria, or another nonpublic portion of this solicitation?
5 | Any access to confidential procurement information that could provide an unfair competitive advantage?
6 | Any former NWMRMC employee separated within the prior year associated with this proposal?
7 | Any other circumstance that could create an actual or apparent conflict or impair impartiality?
C. SUPPORTING DOCUMENTATION
# | Document / Evidence | Status | File name or explanation
1 | Signed disclosure and attestation
2 | Ownership and control disclosure
3 | Subcontractor list and completed disclosures
4 | Written explanation and mitigation plan for each disclosed conflict
5 | Applicable waiver, recusal, advisory opinion, or written resolution
D. VENDOR CERTIFICATION
I certify that the information is complete, true, and correct; all actual, potential, and apparent conflicts have been disclosed; changes will be reported through final payment; and these requirements will be flowed down to each subcontractor at every tier.
Vendor legal name
Authorized representative
Title
Signature
Date

## RFP Exceptions
RFP EXCEPTIONS, ASSUMPTIONS & PROPOSED DEVIATIONS
NWMRMC Maternal-Newborn Phase 1 Readiness RFP ¦ APP-01548
Complete this form for every exception, exclusion, assumption, limitation, dependency, alternate approach, or requested change to the RFP. If the proposal contains no exceptions, select “No Exceptions” below and complete the certification. An undisclosed exception may be treated as acceptance of the applicable RFP requirement.
A. OVERALL EXCEPTION STATUS
Vendor status |  |  |  | Total exceptions listed | 20 | If “No Exceptions” is selected, leave the exception table blank and sign Section C.
B. EXCEPTION DETAIL TABLE
Enter one exception per row. Cite the exact RFP section, appendix, item number, specification, or contract provision. Explain what cannot be accepted, why, the proposed alternative, and any effect on price, schedule, performance, warranty, licensing, security, support, or grant compliance. Attach additional technical or contractual documentation when needed.
Exception # | Category | RFP Section / Item | Requirement or Term | Exception / Requested Change | Reason / Business Justification | Proposed Alternative | Price Impact ($) | Schedule Impact | Attachment / Reference
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
C. VENDOR CERTIFICATION
The vendor certifies that all exceptions, exclusions, assumptions, contingencies, dependencies, alternate approaches, proposed substitutions, and requested changes are fully disclosed in this worksheet and the proposal. Except for items expressly listed above, the vendor accepts and will comply with the RFP requirements. If “No Exceptions” is selected, the vendor certifies that its proposal contains no exceptions or requested deviations.
Vendor legal name
Authorized representative
Title
Signature
Date
D. NWMRMC EVALUATION USE ONLY
Exception review status | Accepted / Rejected / Clarification Required
Evaluator comments
Reviewer and date

## Certifications
FORM D - VENDOR CERTIFICATIONS
Select Yes or No for each certification. Explain every No response.
# | Certification | Yes / No | Comments required if No
1 | Proposal is valid for at least 120 days.
2 | All statements are true and complete.
3 | All actual, apparent, and organizational conflicts have been disclosed.
4 | The proposer and proposed principals/subconsultants are not knowingly suspended, debarred, or excluded.
5 | No collusion or improper communication occurred.
6 | The proposer will comply with applicable 2 CFR Part 200, award, state, and NWMRMC requirements.
7 | The proposer acknowledges this is a professional-services/readiness procurement and does not authorize construction.
8 | All addenda have been acknowledged.
Authorized name and title
Signature
Date
Addenda acknowledged

## Evaluation Criteria
EVALUATION & SELECTION CRITERIA
Published scoring criteria from APP-01548 RFP draft.
Criterion | Points | Evaluator Notes
Understanding of project, grant limits, and active maternal-newborn operations | 15
Technical approach and completeness | 25
Healthcare and maternal-newborn qualifications and relevant experience | 20
Key personnel, disciplines, licenses, and availability | 15
Schedule, project controls, quality assurance, and closeout capability | 10
Cost reasonableness and overall value | 10
Participation/outreach to small and disadvantaged business categories and labor-surplus-area firms | 5
TOTAL | 100